## Instructions
Sprint Planning — Instructions & Legend
COSC2408 Programming Project 1
What this workbook is for
This is the detailed HOW for next sprint — the task-by-task breakdown, owner, timing and sequencing. It is a separate deliverable from your Sprint Playback slide 7 ("What's Next"), which only states WHAT you're promising. This workbook is where that promise gets broken down into real, assigned, time-estimated tasks.
The 240-minute rule
Every team member must be assigned at least 240 minutes (4 hours) of tasks per week, for every week of the upcoming sprint. Estimate time at a junior-practitioner level — the same standard used for your weekly task board (e.g. a straightforward API endpoint with tests is ~30 minutes, regardless of how long it actually takes you in practice). The Weekly Workload Check tab totals this automatically and flags anyone under the minimum.
How to use the Task Plan & Gantt tab
1. Delete the yellow example row once you understand the format — it is not a real task.
2. Add one row per task: name it, assign an Owner, estimate the minutes, set the Week (1–3), the Start Day WITHIN that week (1 = Monday, 5 = Friday) and the Duration in days.
3. The Gantt bar on the right fills in automatically based on Start Day and Duration — you don't edit it directly.
4. Use Dependencies to note if a task can't start until another Task ID is done.
5. Update Status as the sprint progresses — this tab doubles as your working plan, not just a one-off submission.
Editable vs computed
Only the white cells in the Task Plan & Gantt tab are for you to fill in (Task ID through Status). The Gantt bars and everything on the Weekly Workload Check tab are computed automatically — don't type into them. You can change the roles by maunally typing into Column C (owner) and then using the same valueein the Weekly Workload check
Submission
Rename this file x - team name - S1W7_ganttplan (e.g. 90 - Food Delivery System - S1W7_ganttplan) and submit alongside your other Week 7 files. It plans the upcoming sprint, so it's due the same week as your Playback.
Colour key
Example row — delete before submitting
Weekly Workload Check: meets the 240-minute minimum
Weekly Workload Check: under the 240-minute minimum

## Task Plan & Gantt
Team ___ — Next-Sprint Task Plan & Gantt ¦ Sprint __ (Weeks __–__)
Every member needs ≥240 min/week. See the Instructions tab before editing.
Task ID | Task Name | Owner | Est. Minutes | Week | Start Day (1=Mon–5=Fri) | Duration (days) | Dependencies | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3
[8 empty] | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
T1 | Design DB schema for tutor-subject matching | Dev 1 | 90 | 3 | 3 | 1 | -

## Weekly Workload Check
Weekly Workload Check — 240 min (4 hrs) minimum per person, per week
Computed automatically from the Task Plan & Gantt tab. Do not edit the numbers directly.
Role | Week 1 (min) | Week 2 (min) | Week 3 (min) | Sprint Total (min) | Sprint Total (hrs)
PM | 0 | 0 | 0 | 0 | 0
Dev 1 | 0 | 0 | 90 | 90 | 1.5
Dev 2 | 0 | 0 | 0 | 0 | 0
UX/Research | 0 | 0 | 0 | 0 | 0
Business/QA | 0 | 0 | 0 | 0 | 0
Green = meets the 240-minute weekly minimum. Red = under the minimum — rebalance tasks in the Task Plan & Gantt tab.